## User stories
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Owner | Muhammad suffian (23866696)
As a user, I want:
|  | No | User stories
|  | 1 | to create the snake game
|  | 2 | the game to visible on screen
|  | 3 | the window to maximized
|  | 4 | the window to minimized
|  | 5 | the window to resize
|  | 6 | to give direction to move snake
|  | 7 | snake to eat apple and become large
|  | 8 | to snake grow when it eats apple
|  | 9 | to speedup the snake when snake become larger
|  | 10 | to change snake speed
|  | 11 | to login before game start
|  | 12 | to close the game when finised

## Snake-game
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Developer | Muhammad suffian (23866696)
No | Level-1 tasks | Level-2 tasks | Level-3 tasks | Priority | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Note
1 | Create a repository for the project on GitHub |  |  | 1 | 100%
2 | Create and update product backlog |  |  | 1 | 100%
3 | Build the snake game as in the product backlog |  |  | 2
3.1 |  | Build the GUI
3.1.1 |  |  | GUI for gameboard |  |  | 100%
3.1.2 |  |  | GUI for login form |  |  | 100%
3.1.3 |  |  | GUI for Snake |  |  | 100%
3.1.4 |  |  | GUI for Smiley |  |  | 100%
class converted to abstract due to some new abstract methods.
Score Board
Snake
Prey
3.2 |  | Build the game logic
3.2.1 |  |  | Snake logic |  |  |  | 100%
3.2.2 |  |  | Prey Logic |  |  |  | 100%
3.2.3 |  |  | Locate Apple |  |  |  | 100%
3.2.4 |  |  | CheckApple |  |  |  | 100%
3.2.5 |  |  | Check Collasion |  |  |  | 100%
3.2.6 |  |  | key pressed events |  |  |  | 100%
4 | Test and deploy the game |  |  | 3 | 0%
5 | Document the game |  |  | 4 | 0%